## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Prashaant C | 2026-07-28 | Admission metrics were not updating correctly when operational filters were applied | Sprint 1 | Prashaant C | Functional | Corrected filter and admission aggregation logic | 2026-07-30 | Closed | Verified admission metrics after applying operational filters
2 | Prashaant C | 2026-07-31 | Department-filtered patient flow metrics were displaying incorrect values | Sprint 1 | Prashaant C | Functional | Fixed department filtering and KPI calculation | 2026-08-03 | Closed | Verified department-specific patient flow analytics
3 | Prashaant C | 2026-08-04 | Bed occupancy percentage was calculated incorrectly | Sprint 1 | Prashaant C | Calculation | Corrected occupancy calculation formula | 2026-08-06 | Closed | Validated occupancy percentage against bed status data
4 | Prashaant C | 2026-08-07 | Available bed count did not correctly reflect current bed status | Sprint 1 | Prashaant C | Functional | Updated available-bed calculation and status handling | 2026-08-08 | Closed | Verified available beds against current bed status
5 | Prashaant C | 2026-08-12 | Some patient state/district locations were not displayed correctly on the geographic map | Sprint 2 | Prashaant C | Data | Standardized patient location data | 2026-08-14 | Closed | Verified geographic patient distribution on the map
6 | Prashaant C | 2026-08-17 | Analytical charts were not refreshing correctly after changing global filters | Sprint 3 | Prashaant C | UI/Functional | Corrected filter propagation and data refresh logic | 2026-08-19 | Closed | Verified chart updates after applying global filters
7 | Prashaant C | 2026-08-20 | Dashboard components did not handle filters returning no matching records correctly | Sprint 3 | Prashaant C | UI | Added appropriate empty-data handling | 2026-08-21 | Closed | Verified dashboard behavior for empty filtered results
8 | Prashaant C | 2026-08-25 | Length-of-stay and operational KPI values were inconsistent with analytical calculations | Sprint 4 | Prashaant C | Calculation | Validated and corrected KPI calculation logic | 2026-08-27 | Closed | Verified KPI values against analytical calculations
9 | Prashaant C | 2026-09-01 | Bed status displayed in the interface was not synchronized correctly after an operational status update | Sprint 5 | Prashaant C | Functional | Updated bed-state handling and UI synchronization | 2026-09-03 | Closed | Verified bed status synchronization after operational updates
10 | Prashaant C | 2026-09-09 | Application did not load correctly in the deployed environment due to configuration/dependency issues | Sprint 6 | Prashaant C | Deployment | Corrected deployment configuration and dependencies | 2026-09-11 | Closed | Verified successful loading of the deployed application

## Sheet2
Logical
User Interface
Maintainability
Standards
Others