## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-001 | As a hospital administrator, I want healthcare operational data to be ingested and stored in a structured relational database so that hospital information can be managed consistently. | Must Have | Standardized healthcare operational data | Prashaant C | Completed
Sprint 1 | Sprint 1 | US-002 | As a hospital administrator, I want patients, departments, doctors, staff, beds, admissions and treatments to be represented through related database entities so that operational information remains connected. | Must Have | US-001 | Prashaant C | Completed
Sprint 1 | Sprint 1 | US-003 | As a hospital administrator, I want SQL analytical views for hospital overview, floor summary and department metrics so that operational KPIs can be retrieved efficiently. | Must Have | US-002 | Prashaant C | Completed
Sprint 2 | Sprint 2 | US-004 | As a hospital administrator, I want a backend API to provide hospital capacity, occupancy, admission and discharge information so that the frontend can access analytical data. | Must Have | US-003 | Prashaant C | Completed
Sprint 2 | Sprint 2 | US-005 | As a hospital administrator, I want an executive command center showing key hospital KPIs so that I can quickly understand the current operational situation. | Must Have | US-004 | Prashaant C | Completed
Sprint 2 | Sprint 2 | US-006 | As a hospital administrator, I want global filters to update dashboard KPIs and analytical components so that I can examine specific operational segments. | Must Have | US-005 | Prashaant C | Completed
Sprint 3 | Sprint 3 | US-007 | As a hospital administrator, I want an interactive floor and bed topology so that I can view hospital resources and bed availability at floor, room and bed level. | Must Have | US-004 | Prashaant C | Completed
Sprint 3 | Sprint 3 | US-008 | As an operations user, I want to view bed states such as Available, Occupied, Cleaning and Maintenance so that resource status can be monitored operationally. | Must Have | US-007 | Prashaant C | Completed
Sprint 3 | Sprint 3 | US-009 | As an operations user, I want bed status updates to be recorded as operational events so that changes can be audited. | Should Have | US-008 | Prashaant C | Completed
Sprint 4 | Sprint 4 | US-010 | As a hospital administrator, I want patient flow analytics from registration through admission, bed allocation, treatment and discharge so that patient movement through the hospital can be understood. | Must Have | US-005, US-006 | Prashaant C | Completed
Sprint 4 | Sprint 4 | US-011 | As a hospital administrator, I want length-of-stay and discharge delay analytics so that prolonged patient stays and operational delays can be identified. | Must Have | US-010 | Prashaant C | Completed
Sprint 4 | Sprint 4 | US-012 | As a hospital administrator, I want bed turnover analytics so that bed reassignment and resource utilization can be monitored. | Should Have | US-007, US-010 | Prashaant C | Completed
Sprint 5 | Sprint 5 | US-013 | As a hospital administrator, I want physician workload and workforce deployment analytics so that clinical workload and patient-to-staff relationships can be assessed. | Should Have | US-002, US-010 | Prashaant C | Completed
Sprint 5 | Sprint 5 | US-014 | As a hospital administrator, I want clinical diagnostics and service throughput analytics so that procedures and diagnostic activity can be monitored. | Should Have | US-002, US-010 | Prashaant C | Completed
Sprint 5 | Sprint 5 | US-015 | As a hospital administrator, I want accommodation tier utilization analytics for Basic, Elite and Premium rooms so that resource consumption across room categories can be compared. | Should Have | US-007 | Prashaant C | Completed
Sprint 6 | Sprint 6 | US-016 | As a hospital administrator, I want institutional turnover and revenue analytics so that accommodation billing and clinical procedure revenue can be monitored. | Must Have | US-010, US-015 | Prashaant C | Completed
Sprint 6 | Sprint 6 | US-017 | As a hospital administrator, I want daily billed revenue and department revenue contribution views so that financial performance can be analyzed over time. | Should Have | US-016 | Prashaant C | Completed
Sprint 6 | Sprint 6 | US-018 | As a hospital administrator, I want risk and anomaly alerts for high occupancy, discharge delays and housekeeping backlogs so that operational issues can be identified early. | Must Have | US-008, US-011 | Prashaant C | Completed
Sprint 7 | Sprint 7 | US-019 | As a hospital administrator, I want geographic catchment analysis of patient origins by state and district so that regional patient concentration can be understood. | Should Have | US-002 | Prashaant C | Completed
Sprint 7 | Sprint 7 | US-020 | As a hospital administrator, I want a chronological operational event log so that admissions, discharges, transfers and bed status changes can be audited. | Must Have | US-009 | Prashaant C | Completed
Sprint 7 | Sprint 7 | US-021 | As a hospital administrator, I want the complete MediOps Pro platform to integrate the database, API, dashboard, analytics and operational modules so that the system provides a unified healthcare operations intelligence solution. | Must Have | US-004, US-010, US-016, US-018, US-019, US-020 | Prashaant C | Completed
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 50 | 5 | 4 | 5 | 4 | 2 | 5 | 5 | 5 | 5 | 6 | 4 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | T-01 | Identify and collect relevant healthcare operational datasets | 2026-07-27 | 2026-07-27 | Prashaant C | Data Collection | Completed | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | T-02 | Review dataset structure, columns and data quality | 2026-07-28 | 2026-07-28 | Prashaant C | Data Analysis | Completed | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | T-03 | Load healthcare datasets using Pandas | 2026-07-29 | 2026-07-29 | Prashaant C | Data Processing | Completed | 5 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | T-04 | Validate loaded records and standardize source data | 2026-07-30 | 2026-07-31 | Prashaant C | Data Cleaning | Completed | 6 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | T-05 | Design relational database entities for hospital operations | 2026-08-03 | 2026-08-03 | Prashaant C | Database Design | Completed | 5 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | T-06 | Create patient, department, doctor, staff and room-related tables | 2026-08-04 | 2026-08-04 | Prashaant C | Database Development | Completed | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | T-07 | Create admissions, discharges, bed assignments and treatment tables | 2026-08-05 | 2026-08-05 | Prashaant C | Database Development | Completed | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | T-08 | Establish relationships, foreign keys and operational event records | 2026-08-06 | 2026-08-06 | Prashaant C | Database Validation | Completed | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0
US-003 | T-09 | Develop SQL analytical views for hospital overview, floor and department metrics | 2026-08-07 | 2026-08-07 | Prashaant C | SQL Analytics | Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0
US-003 | T-10 | Validate analytical views and verify KPI calculations | 2026-08-08 | 2026-08-08 | Prashaant C | Analytics Validation | Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | No major impediment | Collected the required healthcare operational datasets and reviewed the available source files
Sprint 1 | Day 2 | No major impediment | Reviewed dataset structure, columns and data quality and identified fields required for the project
Sprint 1 | Day 3 | Minor data-format inconsistencies | Loaded the healthcare datasets using Pandas and standardized the required data formats
Sprint 1 | Day 4 | Missing and inconsistent values were identified during data validation | Reviewed affected records and applied data cleaning and validation procedures
Sprint 1 | Day 5 | No major impediment | Completed initial data cleaning and prepared the standardized data for relational database design
Sprint 1 | Day 6 | No major impediment | Designed the relational database structure for hospital departments, rooms, beds, patients and staff
Sprint 1 | Day 7 | No major impediment | Reviewed the database entity relationships and prepared the required table structure
Sprint 1 | Day 8 | No major impediment | Created patient, department, doctor, staff and room-related database tables
Sprint 1 | Day 9 | Minor relationship validation issues | Created admissions, discharges, bed assignments and treatment tables and validated their relationships
Sprint 1 | Day 10 | No major impediment | Established foreign-key relationships and operational event records
Sprint 1 | Day 11 | No major impediment | Developed SQL analytical views for hospital overview, floor summary and department metrics
Sprint 1 | Day 12 | KPI values required validation against source data | Validated analytical view outputs and corrected KPI calculation logic where required
Sprint 1 | Day 13 | No major impediment | Completed validation of the database and analytical views and prepared the backend integration requirements
Sprint 2 | Day 1 | No major impediment | Developed FastAPI backend structure and configured database connectivity for the MediOps Pro application
Sprint 2 | Day 2 | Minor API response validation issues | Validated API responses against the underlying SQL analytical views and corrected response handling
Sprint 2 | Day 3 | No major impediment | Implemented hospital overview and operational KPI API endpoints
Sprint 2 | Day 4 | No major impediment | Integrated the initial React dashboard with the FastAPI backend
Sprint 2 | Day 5 | Minor filter propagation issue | Corrected global filter handling and verified filtered KPI responses
Sprint 2 | Day 6 | No major impediment | Completed Executive Command Center integration and validated dashboard KPI updates
Sprint 2 | Day 7 | No major impediment | Reviewed backend and frontend integration and completed Sprint 2 validation
Sprint 3 | Day 1 | No major impediment | Designed the interactive floor and bed topology structure
Sprint 3 | Day 2 | No major impediment | Implemented floor and room navigation for the hospital blueprint
Sprint 3 | Day 3 | Bed status synchronization required validation | Implemented Available, Occupied, Cleaning and Maintenance bed states
Sprint 3 | Day 4 | Minor UI state synchronization issue | Corrected bed-state handling between the backend and frontend
Sprint 3 | Day 5 | No major impediment | Implemented bed-level information and patient assignment display
Sprint 3 | Day 6 | No major impediment | Implemented operational bed actions and cleanliness approval workflow
Sprint 3 | Day 7 | No major impediment | Validated floor, room and bed interactions and completed Sprint 3
Sprint 4 | Day 1 | No major impediment | Implemented patient flow analytics covering registration, admission, bed allocation, treatment and discharge
Sprint 4 | Day 2 | No major impediment | Developed length-of-stay analytical calculations
Sprint 4 | Day 3 | Minor KPI validation issue | Validated length-of-stay results against admission and discharge records
Sprint 4 | Day 4 | No major impediment | Implemented discharge delay analytics
Sprint 4 | Day 5 | No major impediment | Implemented bed turnover analytics and reassignment metrics
Sprint 4 | Day 6 | No major impediment | Integrated patient flow and operational analytics into the dashboard
Sprint 4 | Day 7 | No major impediment | Validated patient flow, length-of-stay and bed turnover modules
Sprint 5 | Day 1 | No major impediment | Implemented physician workload analytics
Sprint 5 | Day 2 | No major impediment | Implemented workforce deployment and patient-to-staff analysis
Sprint 5 | Day 3 | No major impediment | Implemented clinical diagnostics and service throughput analytics
Sprint 5 | Day 4 | Minor analytical validation issue | Validated service and workload calculations against database records
Sprint 5 | Day 5 | No major impediment | Implemented accommodation tier utilization analytics for Basic, Elite and Premium rooms
Sprint 5 | Day 6 | No major impediment | Integrated workforce, clinical service and accommodation analytics
Sprint 5 | Day 7 | No major impediment | Completed Sprint 5 validation and reviewed analytical outputs
Sprint 6 | Day 1 | No major impediment | Implemented institutional turnover and revenue calculations
Sprint 6 | Day 2 | No major impediment | Implemented accommodation billing and clinical procedure revenue analytics
Sprint 6 | Day 3 | Revenue calculations required validation | Validated turnover and billing calculations against room tariffs and procedure costs
Sprint 6 | Day 4 | No major impediment | Implemented daily billed revenue and department revenue contribution views
Sprint 6 | Day 5 | No major impediment | Implemented operational risk and anomaly alert conditions
Sprint 6 | Day 6 | Minor alert validation issue | Validated occupancy saturation, discharge delay and housekeeping backlog conditions
Sprint 6 | Day 7 | No major impediment | Completed financial and risk intelligence integration
Sprint 7 | Day 1 | No major impediment | Completed geographic catchment and operational audit modules, performed final integration validation and finalized the MediOps Pro platform

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-07-27 | 2026-08-08 | Prashaant C | Start validating data and documenting requirements before development | Stop proceeding with unvalidated source data | Continue structured data cleaning and relational database design | Collected and standardized healthcare data, created the relational database structure and developed the initial SQL analytical views
2 | Sprint 2 | 2026-08-10 | 2026-08-16 | Prashaant C | Start validating API responses against database results during development | Stop making backend changes without checking their effect on frontend data | Continue separating backend API logic from frontend presentation | Implemented FastAPI backend services, connected the database and integrated the Executive Command Center with the frontend
3 | Sprint 3 | 2026-08-17 | 2026-08-23 | Prashaant C | Start validating bed-state changes across both backend and frontend | Stop testing UI components without verifying their underlying operational state | Continue maintaining clear separation between hospital resource data and interface components | Implemented the interactive floor and bed topology, bed states and operational bed management actions
4 | Sprint 4 | 2026-08-24 | 2026-08-30 | Prashaant C | Start testing analytical calculations against source admission and discharge records | Stop relying only on visual dashboard outputs for validation | Continue using operational KPIs to support healthcare decision analytics | Implemented patient flow, length-of-stay, discharge delay and bed turnover analytics and validated the results
5 | Sprint 5 | 2026-08-31 | 2026-09-06 | Prashaant C | Start validating analytical outputs against the underlying relational data | Stop treating workforce and clinical service metrics as isolated outputs | Continue integrating multiple operational datasets into unified analytics | Implemented physician workload, workforce deployment, clinical service throughput and accommodation tier utilization analytics
6 | Sprint 6 | 2026-09-07 | 2026-09-13 | Prashaant C | Start validating financial and risk indicators using defined project calculations | Stop making financial and operational analytics independent of the decision-support layer | Continue integrating operational indicators with actionable intelligence | Implemented institutional turnover, revenue analytics and risk alerts and validated the resulting indicators
7 | Sprint 7 | 2026-09-14 | 2026-09-14 | Prashaant C | Start performing complete end-to-end validation before final deployment | Stop making major structural changes during final integration | Continue maintaining an integrated and auditable healthcare operations platform | Completed geographic catchment and audit intelligence, performed final integration validation and finalized the MediOps Pro platform